## GlobalParts - Carpenters
Global Parts - Transition Status Tracker
[5 empty] | Status as on |  | 2021-11-02
Transition Timelines- 6 days, Shadow support - 1 Day
[5 empty] | Start Date |  | 2021-10-22
End Date
Total Sessions /Topics |  | Sub- Topics Planned | SubTopics Completed (till date) | Topics Remaining # | % Coverage of Total
11 |  | 37 | 28 | 9 | 75.68%
S. No | Topic | Sub-topic | # Days | Start Date | End Date | Status | Attendees | Trainer | Hands on Status
1 | Global Parts | Overview of Global Parts application | Day 1 | 2021-10-22 | 2021-10-22 | Completed | Ragulragavendra | Keerthivasan | Planned
1 | Parts screen | 1. Search for a part number using filters |  |  |  | Completed | Ragulragavendra | Keerthivasan | Completed
|  | 2. View parts screen |  |  |  | Completed | Ragulragavendra | Keerthivasan | Completed
|  | 3.CN tariff |  |  |  | Completed | Ragulragavendra | Keerthivasan | Planned
|  | 4. ADD/CVD admissibility |  |  |  | Completed | Ragulragavendra | Keerthivasan | Completed
|  | 5. Overall audit data |  |  |  | Completed | Ragulragavendra | Keerthivasan | Completed
|  | 6. Sets | Day 2 | 2021-10-27 | 2021-10-27 | Completed | Ragulragavendra | Keerthivasan | Planned
|  | 7. Alternate part number |  |  |  | Completed | Ragulragavendra | Keerthivasan | Completed
|  | 8. timeline |  |  |  | Completed | Ragulragavendra | Keerthivasan | Completed
|  | 9. PGA linking to MID |  |  |  | Completed | Ragulragavendra | Keerthivasan | Completed
|  | 10. Origin Section |  |  |  | Completed | Ragulragavendra | Keerthivasan | Completed
|  | 11. Supplier Section |  |  |  | Completed | Ragulragavendra | Keerthivasan | Completed
|  | 12. Mass Update Section |  |  |  | Completed | Ragulragavendra | Keerthivasan | Pending
2 | Dashboard screen | 1. Marking customer as favorite | Day 3 | 2021-10-27 | 2021-10-27 | Completed | Ragulragavendra | Keerthivasan | Completed
|  | 2. Filter the favorite customers in the dashboard |  |  |  | Completed | Ragulragavendra | Keerthivasan | Completed
|  | 3. Sort the favorite customers in the dashboard from (A-Z) |  |  |  | Completed | Ragulragavendra | Keerthivasan | Completed
3 | Entity management screen | 1. Search for a customer using filters | Day 4 | 2021-10-28 | 2021-10-28 | Completed | Ragulragavendra | Keerthivasan | Completed
|  | 2. Sorting customers in the entity management screen |  |  |  | Completed | Ragulragavendra | Keerthivasan | Completed
|  | 3. Mark/unmark customer as favorite |  |  |  | Completed | Ragulragavendra | Keerthivasan | Completed
|  | 4. Entity management screen of a customer with location and supplier codes which are linked to the account numbers |  |  |  | Completed | Ragulragavendra | Keerthivasan | Completed
4 | HIVE upload screen | 1. HIVE upload filters | Day 5 | 2021-10-28 | 2021-10-28 | Completed | Ragulragavendra | Keerthivasan | Completed
|  | 2. HIVE upload functionality |  |  |  | Completed | Ragulragavendra | Keerthivasan | Completed
|  | 3. HIVE upload summary |  |  |  | Completed | Ragulragavendra | Keerthivasan | Completed
|  | 4. Basic & basic templates |  |  |  | Completed | Ragulragavendra | Keerthivasan | Completed
5 | Account management screen | Account roles: UPS broker agent | Day 6 | 2021-11-01 | 2021-11-01 | Completed | Ragulragavendra | Keerthivasan | Completed
|  | UPS broker agent admin role |  |  |  | Completed | Ragulragavendra | Keerthivasan | Completed
6 | Postman (API Testing) | Classify search API | Day 7 | 2021-11-02 | 2021-11-02 | Completed | Ragulragavendra | Keerthivasan | Planned
7 | Automation | Automation CRAFT Framework Overview |  |  |  | Pending | Ragulragavendra | Keerthivasan | Planned
|  | Automation setup |  |  |  | Pending | Ragulragavendra | Keerthivasan | Planned
|  | Script coverage & execution walkthrough |  |  |  | Pending | Ragulragavendra | Keerthivasan | Planned
|  | Test Results validation |  |  |  | Pending | Ragulragavendra | Keerthivasan | Planned
|  | CI/CD DevOps process |  |  |  | Pending | Ragulragavendra | Keerthivasan | Planned
|  | ADO Git repository & Build pipeline |  |  |  | Pending | Ragulragavendra | Keerthivasan | Planned
8 | Azure DevOps | Test Execution | Day 8 | 2021-11-11 | 2021-11-11 | Pending | Ragulragavendra | Keerthivasan | Planned
|  | Test Result updation in ADO |  |  |  | Completed | Ragulragavendra | Keerthivasan | Planned
|  | Managing all the bug and reports in ADO |  |  |  | Pending | Ragulragavendra | Keerthivasan | Planned
9 | Hands-on Review | Clarifications (if any) | Day 9 |  |  | Planned | Ragulragavendra | Keerthivasan | Planned
10 | Work concurrently in the Current and Future Sprint |  |  |  |  | Planned | Ragulragavendra | Keerthivasan | Planned
[6 empty] | Planned | Ragulragavendra | Keerthivasan | Planned
11 | Work Individually in Sprint activities offline (Hand off) |  |  |  |  | Planned | Ragulragavendra | Keerthivasan | Planned
[6 empty] | Planned | Ragulragavendra | Keerthivasan | Planned